2020-21 District 6780 Grant Timeline

- Project Planning

  - President Elect Year – Decide on the project you want to do.

- Application

  - Applications for the District Grants are accepted during the period of November 2019 through January 31, 2020.

  - Grants will be reviewed and announced beginning in January 2020.

- Funding

  - Clubs can expect to get a grant for half of the project cost, up to the club allocation.

  - See the sheet of club allocations for how much your club will possibly receive.

  - Projects which have not been started by October may be cancelled so the funds can be offered to other clubs.

- Execution

  - After your club project has been approved (usually in April), work can begin.

  - Plan for the execution to be completed by March 2020.

- Progress Report

  - A progress report is due on October 1, 2020.

- Completion

  - Project needs to be completed by May 31, 2021.

- Closing Report

  - A closing report with receipts must be submitted upon completion of the project and no later than May 31, 2021.

  - Reimbursement for the matching grant will take place after the closing report is approved.